## Sheet1
Services | Start Build | Finish Build | % Build | Start Testing | Finish Testing | % Testing | Names | Pending | Notes
Initialise Project | 2023-11-04 |  | 100% | 2023-11-04 | 25/04/2023 | 100% | Tiến |  | add font-google, font-awsome, jequery, waypoint, countup, boostraps, setting github
Universal Classes | 2023-11-04 |  | 100% | 2023-11-04 | 25/04/2023 | 100% | Tiến |  | setting css, section
Header | 25/04/2023 | 25/04/2023 | 100% | 25/04/2023 | 25/04/2023 | 100% | Tiến |  | da reposive
Carousel | 13/04/2023 | 20/04/2023 | 100% | 24/05/2023 | 25/05/2023 | 100% | Đào |  | chua test responsive
About | 13/04/2023 | 13/04/2023 | 100% | 13/04/2023 | 13/04/2023 | 100% | Tiến |  | da reposive
Features | 20/04/2023 | 22/04/2023 | 100% | 22/04/2023 | 22/04/2023 | 100% | Đào
Services | 14/04/2023 | 14/04/2023 | 100% | 14/04/2023 | 16/04/2023 | 100% | Tiến |  | test reposive
number | 15/04/2023 | 15/04/2023 | 100% | 25/06/2023 | 26/04/2023 | 100% | Đào |  | chưa responsive
ourplans | 20/04/2023 | 20/04/2023 | 100% | 21/04/2023 | 23/04/2023 | 100% | Tiến |  | da reposive
betterpet | 15/04/2023 | 25/04/2023 | 100% | 25/04/2023 | 26/04/2023 | 100% | Đào |  | chưa responsive + hiệu ứng nút
Testimonials | 21/04/2023 | 21/04/2023 | 100% | 21/04/2023 | 25/04/2023 | 100% | Tiến |  | test reposive
update | 24/05/2023 | 25/04/2023 | 100% | 25/04/2023 | 26/04/2023 | 100% | Đào |  | bị hiệu ứng chạy button khi kéo màn hình
Footer | 22/04/2023 | 23/11/2023 | 100% | 25/04/2023 | 26/04/2023 | 100% | Đào
Dark Theme | 22/04/2023 | 23/04/2023 | 100% | 25/04/2023 | 26/04/2023 | 100% | Tiến
First Test |  |  |  | 27/04/2023 | 28/04/2023 | 100% | Đào & Tiến
Refactor Code | 24/04/2023 | 26/04/2023 | 100% | 26/04/2023 | 28/04/2023 | 100% | Đào & Tiến
Final Test |  |  |  | 27/04/2023 | 28/04/2023 | 100% | Đào & Tiến